## Timeline
NOTE: Activities should align with Project Readiness Review for EP,PP, and MP milestones | [9 empty] | This Is an example of schedule we are open to different formats.
No | Task Name | Duration | Status | 2016 |  |  | 2017
|  |  |  | W50 | W51 | W52 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46
|  |  |  | 11 Dec- 17 Dec | 18 Dec- 24 Dec | 25 Dec- 31 Dec | 1 Jan- 7 Jan | 8 Jan- 14 Jan | 15 Jan- 21 Jan | 22 Jan- 28 Jan | 29 Jan- 4 Feb | 5 Feb- 11 Feb | 12 Feb- 18 Feb | 19 Feb- 25 Feb | 26 Feb- 4 Mar | 5 Mar- 11 Mar | 12 Mar- 18 Mar | 19 Mar- 25 Mar | 26 Mar- 1 Apr | 2 Apr- 8 Apr | 9 Apr- 15 Apr | 16 Apr- 22 Apr | 23 Apr- 29 Apr | 30 Apr- 6 May | 7 May- 13 May | 14 May- 20 May | 21 May- 27 May | 28 May- 3 Jun | 4 Jun- 10 Jun | 11 Jun- 17 Jun | 18 Jun- 24 Jun | 25 Jun- 1 Jul | 2 Jul- 8 Jul | 9 Jul- 15 Jul | 16 Jul- 22 Jul | 23 Jul- 29 Jul | 30 Jul- 5 Aug | 6 Aug- 12 Aug | 13 Aug- 19 Aug | 20 Aug- 26 Aug | 27 Aug- 2 Sep | 3 Sep- 9 Sep | 10 Sep- 16 Sep | 17 Sep- 23 Sep | 24 Sep- 30 Sep | 1 Oct- 7 Oct | 8 Oct- 14 Oct | 15 Oct- 21 Oct | 22 Oct- 28 Oct | 29 Oct- 4 Nov | 5 Nov- 11 Nov | 5 Nov- 11 Nov
1 | Transact updated document in FPT | 1 Day | Done | bar: 2016 W50
2 | Final list of parts to tool/ Order Tolling released | 4 Day | Done | bar: 2016 W51 to 2017 W1
3 | FAR orders released | 4 Day | Done | bar: 2017 W2 to 2017 W5
4 | CM to order the tools (48 Tools) | 3 Day | Done | bar: 2017 W2 to 2017 W3
5 | Tool Approval | 6 w | Ongoing | bar: 2017 W2 to 2017 W15
6 | Tools at supplier | 13 W | Ongoing | bar: 2017 W5 to 2017 W17
7 | Mec, part verification | 8 w | bar: 2017 W11 to 2017 W18
8 | FAR, Mech part to Transact | 5 w | bar: 2017 W16 to 2017 W20
9 | FAR report | 5 w | bar: 2017 W17 to 2017 W21
10 | FAR approval | 6 w | bar: 2017 W18 to 2017 W23
11 | Material purchasing for FAS | 21 w | Ongoing | bar: 2017 W8 to 2017 W24
12 | Test development | 17 w | Ongoing | bar: 2017 W6 to 2017 W22
13 | EP [ Early Production] , 160 units Generic | 2 w |  | 2017 W25: EP ( Gen ); 2017 W27: Partial ship 30 units within ww25
14 | TransAct Validation Testing, Safety file EMC etc. | 6 w | bar: 2017 W27 to 2017 W32
15 | EP approval by Transact | 1 w | bar: 2017 W33
16 | PP [ Pre Production] , all documented , 320 units Generic | 2 w | bar: 2017 W34 to 2017 W35
17 | Approval by Transact to go TO MP | 1 w | bar: 2017 W36
18 | MP [Mass production] , | 5 w | bar: 2017 W37 to 2017 W41
19 | CCM/Safe Launch Develop and Deployed | 10 w | bar: 2017 W19 to 2017 W46
***Note***

## Tooling Status Tracker
CM TOOLING STATUS SUMMARY
Chart Data Table
Status | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23
Develop
Tool design
Tool Submitted
DesignOK
Not Develop
PO_Released
Waiting PO
Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TACT owns | Week 1: 15; Week 2: 15; Week 3: 16; Week 4: 16; Week 5: 16; Week 6: 17; Week 7: 17; Week 8: 17; Week 9: 17; Week 10: 17

## Tooling status
[7 empty] | TACT Decision and comment |  |  |  | Tooling Detail
Item no | Type | Part # | Description | Supplier | Drawing Rev Up date | ProE | Tooling Cost | TACT PO # | Tooling Status | TACT Eng Comment | Comment | Category | Cavity

## FAR Status Tracker
CM FAR STATUS SUMMARY
POS 9000 28-10487
Chart Data Table
Status | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29
On Schedule
Waiting Plan Date
Submission On Time
Submission Late
Submitted to CM
Rejected By CM
Submitted to TACT
Rejected By TACT
Approved
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## BOM Material - FAR
Description | Item | Rev | CM PN | QPA | MOQ | Supplier | TACT Directed Supplier | Tooling | FAR Required | FAR Commit Date | FAR Submit Date | FAR Status | FAR Shipper Tracking # | TACT FAR # | Notes
M9--- DEFAULT CONFIG AM-23 | CFG-9000_T2 | C |  | - |  | Document | No | No | No | [5 empty] | -
FLASH PROGRAMMING SPECIFICATION | 28-10951 | - |  | 1 |  | Document | No | No | No | [5 empty] | -
CONFIG-M9--- W/PNP ON EPSON/PARALLEL 8-/4- POS/NCR PAPER (AM-23) | CFG9001PE_101 | A |  | 1 |  | Document | No | No | No | [5 empty] | -
TEST REQUIREMENTS: IN-CIRCUIT (GENERIC) | 98-09186 | - |  | - |  | Document | No | No | No | [5 empty] | -
TEST REQUIRMENTS: FUNCTIONAL (GENERIC) | 98-09187 | C |  | - |  | Document | No | No | No | [5 empty] | -
FPGA Implementation Specification | 28-10592L | - |  | - |  | Document | No | No | No | [5 empty] | -
Schematic - POS 9--- Controller | 28-10603L | - |  | - |  | Document | No | No | No | [5 empty] | -
Construction Drawing - POS 9--- Controller | 28-10605L | C |  | - |  | Document | No | No | No | [5 empty] | -
FLASH PROGRAMMING SPECIFICATION | 28-10951 | - |  | 0 |  | Document | No | No | No | [5 empty] | -
SCHEMATIC-M280 36 PIN PAR IF | 28-04030 | B |  | 0 |  | Document | No | No | No | [5 empty] | -
CONSTRUCTION-M280 36 PIN PAR I/F | 28-06471L | B |  | 0 |  | Document | No | No | No | [5 empty] | -
RESISTOR-THK FILM -6-3 5% 1.2K OHM | 99-04055-122L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
RESISTOR-THK FILM -6-3 5% 75 OHM | 99-04055-750L | A |  | 12 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
RESISTOR-THK FILM -8-5 - OHM | 99-04056-000L | A |  | 9 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
RESISITOR-THK FILM -8-5 5% 1-- OHM | 99-04056-101L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Resistor - 12- Ohm 5% -8-5 RoHS | 99-04056-121L | - |  | 3 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
RESISTOR-THK FILM -8-5 5% 5.6K OHM | 99-04056-562L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
RESISTOR-THK FILM 1-- OHM 5% 12-6 | 99-04057-101L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
RESISTOR-THK FILM 2512 5% 1.3 OHM | 99-04058-1R3L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Resistor - -.4 ohm 1/2W 2-1- 1% RoHS | 99-04058-R40L | - |  | 4 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
CAPACITOR--6-3 5-V 2-% X7R .-1UF | 99-04060-103L | A |  | 6 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
HEADER-2MM VERTICAL 4 POS | 99-04067-4L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
HEADER-2MM VERTICAL 5 POS | 99-04067-5L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
HEADER-2MM VERTICAL 6 POS | 99-04067-6L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
CONNECTOR-2MM 7 POS NATURAL | 99-04067-7L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
HEADER-MOLEX MICROFIT 4 POS | 99-04068L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
CONNECTOR-PAK5- VERTICAL PLUG 4-POS | 99-04069-40L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
CONNECTOR-LIF 1.25MM 28POS | 99-04071L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
TRANSISTOR-SMALL SIGNAL NPN | 99-04082L | A |  | 3 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
IC-VOLTAGE REGULATOR ADJUSTABLE | 99-04095L | A |  | 2 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
IC-VOLTAGE REGULATOR LDO 3.3V | 99-04097L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
HEADER - VERTICAL .1 INCH 4POS | 99-04110-4L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
TRANSISTOR - FET P-CHANNEL 8A | 99-04112L | A |  | 2 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
RESISTOR-THK FILM -6-3 1% 1K OHM | 99-04121-1001L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
RESISTOR-THK FILM -6-3 1% 24- OHM | 99-04121-2400L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
RESISTOR - THK FILM -6-3 1% 62- OHM ROHS | 99-04121-6200L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
RESISTOR - 8.2K 1% -6-3 RoHS | 99-04121-8201L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Resistor - 1-- Ohm 5% 121- RoHS | 99-04777-101L | - |  | 3 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
LED-SMT -6-3 RED | 99-05082L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
LED-SMT -6-3 GRCMN | 99-05084L | A |  | 2 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
DIODE-TVS ARRAY TSOP-6 | 99-05696L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Ferrite - -8-5 1---ohm@1--MHz RoHS | 99-05715L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
FERRITE - -6-3 1---ohm@1--MHz RoHS | 99-05717L | - |  | 17 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
TRANSISTOR-FET DUAL N CHANNEL 2.5A | 99-05731L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
CONNECTOR-USB VERTICAL | 99-05736L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
FUSE-3A 125V TIME DELAY | 99-05944L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Resistor - 11K 1% -8-5 RoHS | 99-05953-113L | - |  | 2 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Chip - Res Array -4-2x4 1K Ohm RoHS | 99-05955-102L | - |  | 3 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
CHIP-RES ARRAY -4-2X4 ISO 47 OHM | 99-05955-470L | A |  | 9 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
FERRITE-998 OHMS 1--MHZ RADIAL | 99-05970L | A |  | 2 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
CONNECTOR-6 POS FFC THT RA | 99-05972-06L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
TRANSIENT SUPRESSOR-26V .3J -8-5 | 99-05976L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
SWITCH-TACT R/A THT | 99-05978L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
CONNECTOR-2 POS VERTICAL THT | 99-05979L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
CAPACITOR -MLC -4-2 16V 2-% X7R -.-1UF ROHS | 99-06747-103L | - |  | 14 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Capacitor - MLC 33pf 5% 16V NPO -4-2 RoHS | 99-06747-330L | - |  | 2 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
CAPACITOR - MLC -4-2 6.3V 2-% X5R -.1UF ROHS | 99-06748-104L | - |  | 83 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
CAPACITOR - MLC -4-2 5-V 2-% X7R -.--1UF ROHS | 99-06752-102L | - |  | 8 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Capacitor - MLC 68-pf 5% 5-V X7R -4-2 RoHS | 99-06758-681L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
IC - Microprocessor MCF5253 225 Pin PBGA RoHS | 99-06767L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
IC - ADJUSTABLE STEP DOWN SWITCHING REGULATOR RoHS | 99-07840L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
RECTIFIER - SCHOTTKY 3A 4-V RoHS | 99-07843L | - |  | 3 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Resistor - 1M 5% -4-2 RoHS | 99-08379-106L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Resistor - 2-K 5% -4-2 RoHS | 99-08379-203L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Resistor - Thick Film 2.2K Ohm 5% -4-2 RoHS | 99-08379-222L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Resistor - 2.4K 5% -4-2 RoHS | 99-08379-242L | - |  | 2 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Resistor - 47 ohm 5% -4-2 RoHS | 99-08379-470L | - |  | 4 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Resistor - 4.7K 5% -4-2 RoHS | 99-08379-472L | - |  | 17 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
RESISTOR- 82- ohm 5% -4-2 RoHS | 99-08379-821L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
SDRAM 1Mx16x4 166Mhz 6-pin FBGA RoHS | 99-08385L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Transient Supressor 3.3V .3J -8-5 RoHS | 99-08389L | - |  | 2 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
IC - Reset Controller 3.-6V SOT23 - ADM1818 RoHS | 99-08390L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
IC - Dual Comparators TSSOP8 RoHS | 99-08393L | A |  | 2 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
IC - Octal Line Driver 74LVC541 TSSOP-2- RoHS | 99-08394L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
I.C.- CMPROM- Serial- 8K TSSOP RoHS | 99-08397L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Resistor - 1K 1% -4-2 RoHS | 99-08403-102L | - |  | 14 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Resistor - 1-K 1% -4-2 RoHS | 99-08403-103L | - |  | 37 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Resistor - 1.37K 1% -4-2 RoHS | 99-08403-1371L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Resistor - 2.32K 1% -4-2 RoHS | 99-08403-2321L | - |  | 4 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
RESISTOR-23.2K 1% -4-2 | 99-08403-2322L | - |  | 2 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Resistor - 2.74K 1% -4-2 RoHS | 99-08403-2741L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Resistor - 3.32K 1% -4-2 RoHS | 99-08403-3321L | - |  | 5 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Resistor - 4.-2K Ohm 1% -4-2 RoHS | 99-08403-4021L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
RESISTOR-THK FILM -4-2 1% 4-.2K | 99-08403-4022L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Resistor - Thick Film 5.49K Ohm 1% -4-2 RoHS | 99-08403-5491L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
RESISITOR-5.6K 1% -4-2 | 99-08403-5601L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
RESISTOR-6.-4K 1% -4-2 ROHS | 99-08403-6041L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Resistor - 68- 1% -4-2 RoHS | 99-08403-6800L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
CAPACITOR AL ELECT 35v 33--uf 2-% ROHS | 99-08411L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
DUAL DMOS STEPPER MOTOR DRIVERS | 99-08421L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
LOW POWER CMOS INVERTER 74LVC14 TSSOP14 | 99-08423L | - |  | 3 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
OSCILLATOR - 19.66-8 MHz 1-- PPM ROHS | 99-08426L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
CAPACITOR-AL ELECT 22uf 2-% 35v RADIAL | 99-08427L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Buzzer - 3V RoHS | 99-08448L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
FERRITE--8-5, 1---ohm@1--MHz ROHS | 99-10081L | - |  | 5 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Crystal - 24MHz SMD 3225 | 99-10092L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Altera Cyclone I FPGA EP1C3T144C8 | 99-10093L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Polyfuse 1.5A @ 23deg C 33V SMT | 99-10094L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
IC - LDO Voltage Regulator 15- mA SOT23-5 | 99-10095L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Chip Ferrite Array 4 x 1K@1--Mhz | 99-10096L | - |  | 2 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Common mode choke 9- Ohm @ 1--Mhz 12-6 | 99-10097L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
IC - Octal Bus Transceiver TSSOP2- RoHS | 99-10098L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
IC - Octal Line Driver TSSOP2- RoHS | 99-10099L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Switch R/A Tact RoHS | 99-10100L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Flash 4 Mbit x 16 48 pin FBGA RoHS | 99-10101L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Inductor - 22 uH 1.2A RoHS | 99-10102L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Capacitor - MLCC 4.7 uF 1-% 5-V X5R 12-6 RoHS | 99-10105-475L | - |  | 2 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
Capacitor - MLCC 1- uF 1-% 16V X5R 12-6 RoHS | 99-10106-106L | - |  | 7 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
SWITCH - ROCKER | 99-12335L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE part of Controller Board
RESISTOR-THK FILM -6-3 5% 1-K OHM | 99-04055-103L | A |  | 3 |  | TACT AVL | No | No | No | [5 empty] | EE Part of Interface Board
RESISTOR-THK FILM -6-3 5% 3.3K | 99-04055-332L | A |  | 16 |  | TACT AVL | No | No | No | [5 empty] | EE Part of Interface Board
CAPACITOR--8-5 5-V 2-% X7R .1UF | 99-04061-104L | A |  | 2 |  | TACT AVL | No | No | No | [5 empty] | EE Part of Interface Board
RESISTOR-THK FILM 0603 5% 1K OHM | 99-04055-102L | A |  | 3 |  | TACT AVL | No | No | No | [5 empty] | EE Part of Interface Board
CAPACITOR-0603 50V 10% NPO 47PF | 99-04059-470L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE Part of Interface Board
CAPACITOR-0603 50V 20% X7R .001UF | 99-04060-102L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE Part of Interface Board
CONNECTOR-PAK50 R/A SOCKET 40POS | 99-04070-40L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE Part of Interface Board
CAPACITOR-AL ELEC SMT 16V 20% 22UF | 99-04124L | A |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE Part of Interface Board
CONNECTOR-CENTR RA BAILS PN#4-40 | 99-10088L | - |  | 1 |  | TACT AVL | No | No | No | [5 empty] | EE Part of Interface Board
IC-HEX SCHMITT INVERTER SMT 74HC14 | 99-04146L | A |  | 2 |  | TACT AVL | No | No | No | [5 empty] | EE Part of Interface Board

## RFC Tracker
[10 empty] | CM Process Status |  |  |  |  | CM Phase-In Status
Item | RFC # | RFC Release Date | Description of Change | TACT P/N | Rev | CM P/N | Part Description | Supplier | M/E/B | Quote to TACT? (Y/N) | TACT Quote Approval Date | FAR Submit Date | TACT FAR Approval Date | Released ECO Date | New P/N? (Y/N) | Old P/N | On-hand Inventory Qty (Old P/N) | Inventory Cost | Phase-In Date | Cut-in S/N | Status (Open/Closed) | Comments
Note: Each P/N listed in RFC must have separate line item in tracker
Note on J2: M=Mechanical E=Electrical B=Both

## Action List
OPEN ACTION LIST
Issue | Action Required | Responsible Party | Date |  | Comments
|  |  | Due | Complete
9000 project planning | TSA to confirm 11 week validation plan | TSA | 2017-02-09 | Done | 6 weeks validication plan is confirmed by Transact
9000 project planning | Need PO for EP, PP, MP units and request PO | TSA | 2017-02-03 | Done | PO#42772 28-11584 Generic ( 160 units EP ETA Jun,30 /// 320 units PP ETA Jul,30 //// 800 units MP Sep, 18 ) PO#42775 28-10487 Centronic ( 320 units EP ETA Sep 22 /// 800 units MP ETA Nov,21 )
9000 project planning | Clarify why Nagoya PO is not via CM | TSA | 2017-01-12 | Done
9000 project planning | Propose 200 unit EP | TSA | 2017-01-26 | Done | P/N 28-11584
9000 project planning | Determine Apprroval/FAR process for Transact's directed suppliers | TSA | 2017-02-09 | Done
9000 project planning | Confijrm understanding of udpated timeline | TSA | 2017-01-26 | Done
9000 project planning | Identify common materials with EPIC950/MP2 and update FAR status | CM | 2017-01-27 | Done
9000 project planning | Confirm CM requires FAR 28-10815 ( Blade knife assembly ) only | TSA | 2017-02-09 | Done | Refer to FAR submission flow process
9000 project planning | Remove springs purchasing plan from Omon | CM | 2017-01-25 | Done | Change to Goko vedor
9000 project planning | Confirm Nagoya supply 28-10405 with Ithaca artwork ( 28-10478, 28-10479 ) | CM | 2017-02-09 | Done | Nagoya confirms supply part with printed logo
9000 project planning | Need updated drawing 28-10405 with artwork ( 28-10478, 28-10479 ) | TSA | 2017-02-09 | Done | Received update in RFC#R37168
9000 project planning | Confirm 28-09752 and 28-10980 ( Bearing ) have corrected material | CM | 2017-02-02 | Done | Already confirm vendor refer to MATERIAL: TMS-M5110 (BRONZE, POWDERED METAL (SAE 841); OIL IMPREGNATED WITH NYE SYNTHETIC OIL 180P).
9000 project planning | Which sensor to buy from which supplier 99-04081 | TSA | 2017-01-26 | Done | Supplier ALEPH
9000 project planning | Why PN 28-06479L ( I/F Board )in BOM twice rev A and J | TSA | 2017-02-02 | Done
9000 project planning | Determine alternative supplier for Flat Flex cable (28-04036L) | CM | 2017-02-09 | Done | Using Winxin / Cable is common used with EPIC950 ( FAR22147 )
9000 project planning | Scrup BOM for dupplicate parts to submit FAR one time | CM | 2017-01-12 | Done
9000 project planning | Determine alternative supplier for Tear off ( 28-10316 ) | TSA | 2017-01-25 | Done | Santec
9000 project planning | Confirm labels to be printed by CM | CM | 2017-01-26 | Done | CM should print serial number plate only 28-10487
9000 project planning | Provide Test spec and Test procedure | TSA | 2017-01-26 | Done
9000 project planning | Determine actions for BOM 22-11584 | CM | 2017-01-26 | Done
9000 project planning | CM to propose Flow layout | CM | 2017-02-24 | Done
9000 project planning | TSA confirm correct BOM for Generic | TSA | 2017-02-02 | Done
9000 project planning | CM provide quote for Generic and Centronic | CM | 2017-02-21 | Done | Quote submitted. Confirming price change of some parts against original Quote
9000 project planning | Provide FAR submission date | CM | 2017-02-03 | Done | Pending updated FAR dates from Nagoya
9000 project planning | Update process tooling into Tooling list | CM | 2017-02-03 | Done
9000 project planning | Provide revised Quote for Centronics model | CM | 2017-02-06 | Done
9000 project planning | Provide revised Quote for Generic model | CM | 2017-02-06 | Done
9000 project planning | Add process tool in tool tracker | CM | 2017-02-09 | Done
9000 project planning | Provide spec of F/W programming adaptor for IC U3 of POS9000 controller board | TSA | 2017-02-09 | Done
9000 project planning | CM propose Quote , Brand / Model of Programming device | CM | 2017-03-02 | Done
9000 project planning | Submit Quote and FCT / ICT design , Test plan | CM | 2017-03-02 | Done
9000 project planning | Send Printing Paper for Test development | TSA | 2017-03-02 | Done
9000 project planning | Update all mat'l required in FAR stutus list. | CM | 2017-03-02 | Done
9000 project planning | Confirm 28-28503 ( Maintenance manual ) REV D dwg released under R37170 to include in BOM | TSA | 2017-03-13 | Done | Part is confirmed by TACT not required in BOM
9000 project planning | Provide improved Tool and FAR schedule from Nagoya | CM | 2017-03-24 | Done
9000 project planning | Provide initial CCM that includes requirements , Lesson learnt | CM | 2017-03-22 | Done | Draft were sent
9000 project planning | Implement site tree to organize information and data on the FTP site | CM | 2017-03-22 | Done
9000 Process | Midframe ( 28-15477 ) assembled with at Supplier ( Nagoya ) ? | CM | 2017-03-30 | Done | CM will assemble this part

## Project Readiness Review Chart
Item #1 | Responsible | Item | EP - ~45 | EP | PP | MP | MP + ~90
1 | NPI ENG | Flow | D | D | R | C | -
2 | NPI ENG | FMEA | D | D | R | C | -
3 | NPI ENG | WI | - | D | R/E | E | E
4 | NPI ENG | Process Tooling | D1 | E | C | - | -
5 | MFG ENG | PM Plan | - | - | D | R | E
6 | QA | Control Plan | D | D | R | C | -
7 | QA | IPQC | - | D2 | R/E | E | E
8 | QA | OQA | - | D2 | R/E | E | E
9 | QA | CCM - Process | D | D | R/E | E | ~C
10 | QA | Cosmetic Spec | - | D | R/E | E | E
11 | QA | PQ Acceptance | - | D | R/E | E | E
12 | QA | FPY Tracking | - | D | R/E | E | E
13 | Prod/QA/ME | Training | - | - | D/R/E | E | E
14 | Sourcing | FAR | E | C | C3 | - | -
15 | SQE | CCM - Material | D | E4 | R/E | E | ~C
16 | Test | Test - ICT | D | C | C | - | -
17 | Test | Test - FCT | D | D | C | - | -
18 | Test | Test - Functional | D | D | C | - | -
Legend |  | Notes:
D - Draft |  | 1 - Proposal should be submitted and approved and tooling under fabrication
R - Released/ Ready |  | 2 - Need to develop these tools at this phase during build
E - Executing |  | 3 - FARs for changes to tooling from EP should be resubmitted
C - Complete |  | 4 - Need to start reporting on the first lot off tool

## List for FAR Status (hidden)
Submission Late
Submission On Time
Submitted to HT
Rejected By HT
Submitted to TACT
Rejected By TACT
Approved
Not Applicable